## Zend Bug Report
ZEND BUG REPORT
BUG ID |  |  |  | BUG OVERVIEW |  | ENVIRONMENT | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | SCREENSHOT | OPERATING SYSTEM | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | NOTES | SEVERITY | DEFECT PRIORITY | STATUS
B_Signup_01 | Accept registration without entering Text | Abdelrahman Zedan | 2023-12-12 | If textboxes of password field, first name, last name, or phone number does not contain any of the text, the application accepts registration and a message appears: registration has been completed successfully. |  | Android 12 | 1- press account button 2-press signup button 3- filling all data except Last name field. | Missing data required , please fill all textboxes | لقد تم التسجيل بنجاح | Showstopper | Critical | Abdelrahman Yasser | Closed |  |  |  | Showstopper | Critical | Open
B_Signup_02 | Password is less than 8 Digits | Abdelrahman Zedan | 2023-12-12 | if user enter password less than 8 digits the application accepts registration and a message appears: registration has been completed successfully. |  | Android 12 | 1- press account button 2-press signup button 3- filling password textbox with length less than 8 digits. | error : password length must be more than 8 digits | لقد تم التسجيل بنجاح | Major | High | Abdelrahman Yasser | Closed |  |  |  | Major | High | Resolved
B_Signup_03 | Loading without Action or navigation | Abdelrahman Zedan | 2023-12-13 | after user register and verify E-mail , if doesn't enter any data after that then press confirm , the Application just loading without Any Action. |  | Android 12 | 1- press account button 2-press signup button 3- filling all data and verify Email then navigate to continue missing Textboxes. | if user doen't enter some data such as: bithdate or height or weight or location ,There is no harm in going to the home page and entering it later | Just Loading without action. | Major | Critical | Abdelrahman Yasser | Re op |  |  | Bad Request message Appears | Minor | Medium | Closed
B_Signup_04 | The App accept special characters and spaces and numbers in firstname & lastname box | Abdelrahman Zedan | 2024-01-11 |  |  | Android 12 | 1- press account button 2-press signup button 3- filling fname and Lname with special character or numbers or spaces | من فضلك ادخل الاسماء بشكل صحيح : حروف فقط | تم تسجيل الحساب بنجاح | Showstopper | Critical | Abdelrahman Yasser | Closed |  |  | under review | Low | Low | Re op
B_Login_01 | Invalid password | Abdelrahman Zedan | 13/12/2023 | if user enter invalid password for exist Email the application is just loading |  | Android 12 | 1- press account button 2-press Login button 3- filling password textbox with invalid password for exist Email. | Invalid Email Or Password | Just Loading without action. | Showstopper | Critical | Abdelrahman Yasser | Closed
B_HOME_01 | NO images loaded in tradeMark Section | Abdelrahman Zedan | 2023-12-31 | - |  | Android 12 | IN HOME PAGE | Images Loaded | فشل نحميل الصوره | Low | Medium | Abdelrahman Yasser | Closed
B_EditData_01 | the Age is 0 ! | Abdelrahman Zedan | 2023-12-31 | If user's age less than 1 Year System appear it as 0 |  | Android 12 | Press on Profile button after login | Age appears by days OR cancel appear age | Age is 0 | Major | Medium | Abdelrahman Yasser | Closed |  |  | It is preferable not to show age
B_Visits_01 | The Time is wrong | Abdelrahman Zedan | 2023-12-31 | - |  | Android 12 | 1- login 2-Press on visits button | Correct Time 3:57 am | Wrong TIme 1:57 am | Major | Critical | Abdelrahman Yasser | Closed | The time from server is setting up for UTC, In the production it will set up for saudi locality so it's automatically resolved while production, Also I provide a solution make time change depend on your location automatically (for future plans isA) |  | The Correct time is two hours more
B_EditData_02 | The profile Image is Wrong | Abdelrahman Zedan | 2023-12-31 | If User choose specific picture during register process in edit profile appears another |  | Android 12 | Press on Profile button after login | Correct Image | Another Image OR white Image OR failed to load image | Showstopper | Critical | Abdelrahman Yasser | Closed |  |  | closed for now but depends on another bug , which is Complete sign up
B_Complete_SignUp | Complete Data | George Elamir | 2024-01-01 | If the app colsed without completeing data the app assumed the user completed data automatically |  | Android 12 | Login with not completed data account then colse the app | Open complete signup screen again | login successfully | Showstopper | Critical | Abdelrahman Yasser | Closed
B_EditData_03 | gray screen appears when change location | Abdelrahman Zedan | 2024-01-10 |  |  | Android 12 | Press on Profile button after login then edit data then change location | Loaction changed sucssesfully | gray screen without any action | Showstopper | Critical | Abdelrahman Yasser | Closed |  |  | closed for now but depends on another bug , which is Complete sign up
B_EditData_04 | able to change age less than 12 | Abdelrahman Zedan | 2024-01-10 | If user edit his AGE to number less than 12 after register the system will be accept it ! |  | Android 12 | Press on Profile button after login then edit data then change Age | Can't change age ro number less than 12 years | تم التحديث بنجاح | Showstopper | Critical | Abdelrahman Yasser | Closed
B_RatingApp_01 | App doesn't accept comments ! | Abdelrahman Zedan | 2024-01-11 | if user try to write comment after rating , the app prevent it |  | Android 12 | sign in then go to gyms then choose one of then then press rate | Accpet comment | لا يمكن ارسال تعليق فارغ | Showstopper | Critical | Abdelrahman Yasser | Closed
WEB BUGS WEB BUGS WEB BUGS WEB BUGS
B_OwnerDashBoardEditGYMS_01 | Delay in editing and strange Text format appearance | Abdelrahman Zedan | 2024-03-04 | when data of gyms in owner dashboard is edited , the Website loading In a very strange and wobbly way + description texts appear in a strange format | https://drive.google.com/file/d/1B9-fjk65Z3rlQ4UZISBSnwSa63e-QEvt/view?usp=sharing | Chrome | login in owners dashboard via : https://zndgym.com/owners/dashboard/gyms/1 | normal format of description is appeared | HTML CODE format is appeared | Minor | Medium | George Elamir | Open
B_OwnerDashBoardEditGYMS_02 | I can't Delete Gyms | Abdelrahman Zedan | 2024-03-04 | Owners should be able to delete any gym |  | Chrome | login in owners dashboard via : https://zndgym.com/owners/dashboard/gyms | there is Delete button in edit gym page | there is not any button to delete gym | Major | High | George Elamir | Re op
B_OwnerDashBoardADDGYMS_01 | Rank not allowed! | Abdelrahman Zedan | 2024-03-04 | if owner adds gym and choose rank with number 4 for example , app accept it Although we only have 3 ranks (1,2,3). | https://drive.google.com/file/d/10cq1cV9bvQzRn1jlYhXaah4sQ0UO-fKw/view?usp=sharing | Chrome | login in owners dashboard via : https://zndgym.com/owners/dashboard/gyms/40 | Error : There are no ranks other than 1, 2, and 3 | website accept rank 4 | Showstopper | Critical | George Elamir | Open
B_ConfirmationSubscribePage_01 | message warning doesn't appear | Abdelrahman Zedan | 2024-03-09 | when I want to purchase some package , without sign in, the system doesn't appear Any messages | https://drive.google.com/file/d/1nPUsVnqQ8eg1F2zfptQOb6EF3pJwLQ7b/view?usp=sharing | Chrome | go to : https://zndgym.com/packages/subscribe/8 then click confirmation subscribe | "يجب عليك تسجيل الدخول اولا " | NO Actions appears | Low | Medium | George Elamir | Closed
B_Signup_01 | Password is less than 8 Digits | Abdelrahman Zedan | 2024-03-09 | if user enter password less than 8 digits the application accepts registration and a message appears: registration has been completed successfully. |  | Chrome | 1- press account button 2-press signup button 3- filling password textbox with length less than 8 digits. | error : password length must be more than 8 digits | لقد تم التسجيل بنجاح | Showstopper | High | George Elamir | Open
B_EditData_01 | Image doesn't appear | Abdelrahman Zedan | 2024-03-09 | when I click "حسابي" button , i can't see the profile image | https://drive.google.com/file/d/1947HAg5BrIo7-5Vr2n57zUZCNXMUl2hb/view?usp=sharing | Chrome | after sign in go to : https://zndgym.com/account | Image appears | Image doen't Appear | Showstopper | Medium | George Elamir | Resolved |  |  | cannot be testing because it depends on signin
B_EditData_02 | It does not go to the home page after log out | Abdelrahman Zedan | 2024-03-09 | when I click "حسابي" button , then log out the secret information stay appears | https://drive.google.com/file/d/1ZokhjCtLtnaqQyPp-XX5JDcQEnIFouUt/view?usp=sharing | Chrome | after sign in go to : https://zndgym.com/account then log out | go to Home page | stay | Showstopper | High | George Elamir | Resolved |  |  | cannot be testing because it depends on signin
B_Signup_02 | system accept Character with SSN !! | Abdelrahman Zedan | 2024-03-09 | when I enter characters in SSN field it is accepted ! |  | Chrome | https://zndgym.com/register | SSN must be numbers Only | system accept registeriation | Showstopper | High | George Elamir | Open
B_Signup_03 | system doesnt able to signup!!!!!!!! | Abdelrahman Zedan | 2024-04-08 | when I try to signup with correct data the system appers bad request message | https://drive.google.com/file/d/15INpA2LZQg7yTch7shekgsPkz3xfzVmE/view?usp=sharing | Chrome | https://zndgym.com/register | signup successfully | the system appears bad request message | Showstopper | High | George Elamir | Open

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.